## Gantt Chart
PowerView Billing & Tiers System - Project Timeline
1 month: 3 - 31 Aug 2026 ¦ Mon-Fri only ¦ 21 working days ¦ Goal: Ready for Testing (no deploy)
[8 empty] | Week 1 (03/08 - 07/08) |  |  |  |  | Week 2 (10/08 - 14/08) |  |  |  |  | Week 3 (17/08 - 21/08) |  |  |  |  | Week 4 (24/08 - 28/08) |  |  |  |  | Week 5 (31/08 - 31/08)
# | Task | Owner | Detail | Start | End | Days | Status | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
Phase 1: PostgreSQL Schema & Database
1 | 1.1 Migration: TIERS + seed data (free/pro/enterprise) | Backend Dev | CREATE TABLE tiers + INSERT seed data | 03/08 | 03/08 | 1 d | Pending | bar: Mon
2 | 1.2 Migration: DEVICE_SUBSCRIPTIONS + FK | Backend Dev | CREATE TABLE device_subscriptions + FK constraints + indexes | 04/08 | 04/08 | 1 d | Pending | bar: Tue
3 | 1.3 Migration: PAYMENTS + indexes | Backend Dev | CREATE TABLE payments + provider_ref index | 04/08 | 04/08 | 1 d | Pending | bar: Tue
4 | 1.4 SQLAlchemy Models (Tier, Subscription, Payment) | Backend Dev | Python ORM models + relationships | 05/08 | 05/08 | 1 d | Pending | bar: Wed
5 | 1.5 Unit Tests: CRUD + Relationships | Backend Dev | pytest: create/read/update + FK integrity | 05/08 | 05/08 | 1 d | Pending | bar: Wed
Phase 2: InfluxDB Multi-Bucket & Downsampling
6 | 2.1 สร้าง 9 Buckets ตาม Tier | DevOps | power_data_free/pro/enterprise + _1m + _1h variants | 06/08 | 06/08 | 1 d | Pending | bar: Thu
7 | 2.2 ตั้งค่า Retention Policy แต่ละ Bucket | DevOps | 7d/90d/365d (raw), 30d/1y/inf (1m), 1y/3y/inf (1h) | 06/08 | 06/08 | 1 d | Pending | bar: Thu
8 | 2.3 Flux Tasks: Downsampling Raw -> 1m (3 tasks) | Backend Dev | mean() aggregation every 1 min, per tier bucket | 07/08 | 10/08 | 2 d | Pending | bar: Fri to Mon
9 | 2.4 Flux Tasks: Downsampling 1m -> 1h (3 tasks) | Backend Dev | mean() aggregation every 1 hr, per tier bucket | 10/08 | 10/08 | 1 d | Pending | bar: Mon
Phase 3: Telegraf + Redis Data Routing
10 | 3.1 ติดตั้ง Redis Container (Docker Compose) | DevOps | เพิ่ม redis service + volume ใน docker-compose.yml | 10/08 | 10/08 | 1 d | Pending | bar: Mon
11 | 3.2 Redis Tier Cache Logic | Backend Dev | API อัปเดต device tier -> Redis ¦ Telegraf อ่าน tier จาก Redis | 11/08 | 12/08 | 2 d | Pending | bar: Tue to Wed
12 | 3.3 แก้ไข telegraf.conf: Route ข้อมูลตาม Tier | Backend Dev | Starlark/Execd processor: อ่าน Redis -> เลือก output bucket | 12/08 | 13/08 | 2 d | Pending | bar: Wed to Thu
13 | 3.4 ทดสอบ Data Routing (Free/Pro/Enterprise) | QA/Dev | ส่ง mock data -> ตรวจว่าลง Bucket ถูกต้อง | 13/08 | 13/08 | 1 d | Pending | bar: Thu
Phase 4: Backend API - Billing & Subscription
14 | 4.1 GET /tiers (ดึงรายการแพ็คเกจ) | Backend Dev | return tier ทั้ง 3 + ราคา + feature flags | 13/08 | 13/08 | 1 d | Pending | bar: Thu
15 | 4.2 GET /devices/{id}/subscription | Backend Dev | ดึง subscription ปัจจุบัน + expires_at | 13/08 | 13/08 | 1 d | Pending | bar: Thu
16 | 4.3 POST /billing/checkout-session | Backend Dev | สร้าง Stripe Checkout Session (price_id + metadata) | 14/08 | 17/08 | 2 d | Pending | bar: Fri to Mon
17 | 4.4 POST /billing/webhook (Stripe Webhook) | Backend Dev | Handle: checkout.session.completed, invoice.paid, subscription.deleted | 17/08 | 18/08 | 2 d | Pending | bar: Mon to Tue
18 | 4.5 Webhook Handler: Update Sub + Payment + Redis | Backend Dev | ACID Transaction: payment -> subscription -> Redis cache | 18/08 | 18/08 | 1 d | Pending | bar: Tue
19 | 4.6 GET /billing/history | Backend Dev | ดึง payments ของ user พร้อม pagination | 18/08 | 18/08 | 1 d | Pending | bar: Tue
20 | 4.7 Subscription Expiry Cron Job | Backend Dev | Daily check: expired -> downgrade Free + ย้าย Bucket | 19/08 | 20/08 | 2 d | Pending | bar: Wed to Thu
Phase 5: Stripe Payment Gateway Integration
21 | 5.1 Stripe Account + Product/Price Setup | Admin | Products: Pro Monthly/Yearly, Enterprise Monthly/Yearly | 19/08 | 19/08 | 1 d | Pending | bar: Wed
22 | 5.2 Register Webhook Endpoint + Signing Secret | Backend Dev | Stripe Dashboard: set webhook URL + get signing secret | 20/08 | 20/08 | 1 d | Pending | bar: Thu
23 | 5.3 Checkout Session + stripe-python SDK | Backend Dev | เชื่อม checkout-session API กับ Stripe SDK | 20/08 | 20/08 | 1 d | Pending | bar: Thu
24 | 5.4 Test Payment Flow (Test Mode) | QA/Dev | Test: success, fail, cancel, renewal, refund | 21/08 | 24/08 | 2 d | Pending | bar: Fri to Mon
25 | 5.5 Stripe Signature Verification (HMAC) | Backend Dev | ป้องกัน webhook ปลอม (stripe.Webhook.construct_event) | 21/08 | 21/08 | 1 d | Pending | bar: Fri
Phase 6: API Query Layer - Tier-Aware Data Access
26 | 6.1 Query เลือก Bucket ตาม Tier | Backend Dev | subscription -> tier -> bucket name -> InfluxDB query | 24/08 | 25/08 | 2 d | Pending | bar: Mon to Tue
27 | 6.2 Downsampled Data Endpoints | Backend Dev | GET /data/1m, GET /data/1h สำหรับกราฟระยะยาว | 25/08 | 25/08 | 1 d | Pending | bar: Tue
28 | 6.3 Feature Gate: Export CSV / API Access | Backend Dev | check tier.allow_export / tier.allow_api ก่อนอนุญาต | 25/08 | 25/08 | 1 d | Pending | bar: Tue
Phase 7: Integration Testing & QA
29 | 7.1 E2E: Free Tier Flow | QA | สมัคร -> real-time -> ย้อนหลัง 7d -> limit 3 devices | 26/08 | 26/08 | 1 d | Pending | bar: Wed
30 | 7.2 E2E: Pro Tier Flow | QA | จ่ายเงิน -> upgrade -> ย้อนหลัง 90d -> export CSV | 26/08 | 26/08 | 1 d | Pending | bar: Wed
31 | 7.3 E2E: Enterprise Tier Flow | QA | จ่ายเงิน -> ย้อนหลัง 1 ปี -> API -> custom alerts | 27/08 | 27/08 | 1 d | Pending | bar: Thu
32 | 7.4 Load Test: 100-500 devices | DevOps | Telegraf + Redis + Multi-Bucket under load | 27/08 | 27/08 | 1 d | Pending | bar: Thu
33 | 7.5 Security Test | QA/Security | Stripe signature, JWT, rate limit, CORS, SQL injection | 28/08 | 28/08 | 1 d | Pending | bar: Fri
Phase 8: Backup, Docs & Test Readiness
34 | 8.1 Backup Script: InfluxDB + PostgreSQL | DevOps | cron ทุก 6 ชม. + rclone sync -> Cloudflare R2 | 28/08 | 28/08 | 1 d | Pending | bar: Fri
35 | 8.2 Disaster Recovery Test (Restore) | DevOps | ทดสอบกู้คืนบน VPS ใหม่ | 28/08 | 28/08 | 1 d | Pending | bar: Fri
36 | 8.3 Terms of Service / SLA (Draft) | Admin/Legal | Free: No SLA ¦ Pro: 99% ¦ Enterprise: 99.9% | 28/08 | 28/08 | 1 d | Pending | bar: Fri
37 | 8.4 อัปเดต Architecture & API Docs | Backend Dev | .md files + Swagger/OpenAPI docs | 31/08 | 31/08 | 1 d | Pending | bar: Mon
38 | 8.5 Test Readiness Review & Handoff | Team | Code review + checklist: ระบบพร้อมเข้า QA/UAT | 31/08 | 31/08 | 1 d | Pending | bar: Mon
Milestones | bar: Mon to Mon
Legend:
Phase 1: PostgreSQL Schema & Database
Phase 2: InfluxDB Multi-Bucket & Downsampling
Phase 3/6: Telegraf, Redis & API Query Layer
Phase 4: Backend API - Billing & Subscription
Phase 5: Stripe Payment Gateway
Phase 7: Integration Testing & QA
Phase 8: Backup, Docs & Test Readiness
Note on K53: DB Schema Ready (05/08)
Note on N53: InfluxDB Buckets Ready (10/08)
Note on Q53: Data Routing Works (13/08)
Note on V53: Billing API Complete (20/08)
Note on X53: Stripe Payments Work (24/08)
Note on Z53: QA Started (26/08)
Note on AC53: Ready for Testing! (31/08)

## Phase Summary
Phase | Name | Working Days | Start | End | Sub-tasks | Owner | Dependencies
Phase 1 | PostgreSQL Schema & Database | 3 days | 3/08 (Mon) | 5/08 (Wed) | 5 | Backend Dev | -
Phase 2 | InfluxDB Multi-Bucket & Downsampling | 3 days | 6/08 (Thu) | 8/08 (Mon) | 4 | DevOps / Backend Dev | Phase 1
Phase 3 | Telegraf + Redis Data Routing | 4 days | 8/08 (Mon) | 13/08 (Thu) | 4 | Backend Dev / DevOps | Phase 2
Phase 4 | Backend API - Billing & Subscription | 6 days | 13/08 (Thu) | 20/08 (Thu) | 7 | Backend Dev | Phase 1 + 3
Phase 5 | Stripe Payment Gateway Integration | 4 days | 18/08 (Mon) | 21/08 (Thu) | 5 | Backend Dev / Admin | Phase 4
Phase 6 | API Query Layer (Tier-Aware Access) | 3 days | 21/08 (Thu) | 25/08 (Mon) | 3 | Backend Dev | Phase 3 + 5
Phase 7 | Integration Testing & QA | 3 days | 25/08 (Mon) | 27/08 (Wed) | 5 | QA / DevOps / Security | All above
Phase 8 | Backup, Docs & Test Readiness | 2 days | 27/08 (Wed) | 28/08 (Thu) | 5 | DevOps / Admin / Team | Phase 7
| TOTAL | 21 working days | 3/08 | 28/08 (+buffer) | 37 | - | Goal: Ready for Testing

## Notes & Risks
Category | Detail
Working Days | Total 21 working days (Mon-Fri only). Weekends excluded.
Team Size | Assumes 1-2 full-time developers. Some phases can overlap with more people.
Parallel Work | Phase 1 (DB) & Phase 2 (InfluxDB) can partially overlap if >1 dev available.
RISK: Stripe | Stripe business verification may take 1-3 days. Register BEFORE Aug 3!
RISK: Telegraf | Starlark/Execd processor may be complex. Do a POC spike first.
RISK: Flux Tasks | Flux language may be deprecated in InfluxDB 3.x. Use 2.x for now, plan migration.
RISK: Load Test | Need a separate VPS for simulating 100-500 devices. Prepare in advance.
Buffer Days | Aug 28 (Thu) is the last scheduled task. Aug 29-31 = 2 buffer days for bug fixes.
Scope | This timeline covers DEVELOPMENT ONLY. Goal = Ready for Testing/QA. Production deployment is NOT included.
Reference | Source document: BILLING_AND_TIERS_SYSTEM.md (PowerView Repository)